## Read me
Construction site management system
Made-up data: every name, amount, shop and date in this file is made up for practice. Replace it with your own.
Yellow cells are inputs: type over them. Green cells hold formulas: do not type over them. Blue rows are headers and totals.
From ravindrabagale.com, Excel course, Excel Business Management Systems. By Ravindra Bagale.
Sheets: Setup, BOQ (progress, this bill), Materials, Labour, Cost report (budget vs actual), RA bill (printable), Dashboard.
Retention % is whatever your contract says; 5% here is only an example. GST and TDS rates are inputs; confirm with your accountant.
Enter measured cumulative quantities, never this-bill quantities; the sheet subtracts earlier bills.

## Setup
Construction Site Management System: Setup (Bagale Constructions, Kolhapur)
Made-up project: a G+1 row house for Shraddha Bagale. Rates, quantities and terms are examples. |  | Cost heads | Trades
As-of date | 2026-10-17 | Materials | Mason
Project | G+1 row house, Kolhapur | Labour | Helper
Client | Shraddha Bagale | Equipment | Carpenter
Retention (as per contract) | 5% | Other | Bar bender
GST on works contract | 18%
TDS by client (194C, firm) | 2%
RA bill no | 3

## BOQ
Bill of quantities and progress
Type the measured cumulative quantity in G and the quantity already billed in previous RA bills in H.
Code | Item | Unit | BOQ qty | Rate (₹) | Amount (₹) | Done qty (cumulative) | Billed qty (previous) | % done | This bill qty | This bill (₹) | Done value (₹)
B01 | Excavation | cum | 180 | 350 |  | 180 | 180
B02 | PCC 1:4:8 | cum | 22 | 5200 |  | 22 | 22
B03 | RCC footings and columns | cum | 48 | 9800 |  | 48 | 40
B04 | RCC slab and beams | cum | 64 | 9500 |  | 40 | 0
B05 | Brickwork 230 mm | cum | 95 | 6200 |  | 30 | 0
B06 | Plaster 12 mm | sqm | 900 | 320 |  | 0 | 0
B07 | Flooring tiles | sqm | 210 | 1150 |  | 0 | 0
B08 | Painting | sqm | 1400 | 140 |  | 0 | 0
Total

## Materials
Materials and site costs (October)
One row per bill. Amount = qty × rate.
Date | Item | Cost head | Qty | Rate (₹) | Amount (₹)
2026-10-01 | Cement (bags) | Materials | 300 | 380
2026-10-02 | Steel (kg) | Materials | 2500 | 62
2026-10-05 | Sand (brass) | Materials | 6 | 6500
2026-10-08 | Bricks | Materials | 9000 | 9
2026-10-09 | Shuttering hire | Equipment | 1 | 42000
2026-10-12 | Cement (bags) | Materials | 250 | 385
2026-10-13 | Aggregate (brass) | Materials | 5 | 4200
2026-10-15 | Mixer hire | Equipment | 1 | 9000
2026-10-16 | Site water and power | Other | 1 | 7500

## Labour
Labour attendance (October)
One row per trade per day. Amount = workers × daily rate.
Date | Trade | Workers | Daily rate (₹) | Amount (₹)
2026-10-01 | Mason | 2 | 900
2026-10-01 | Helper | 6 | 550
2026-10-01 | Carpenter | 2 | 950
2026-10-01 | Bar bender | 2 | 850
2026-10-02 | Mason | 2 | 900
2026-10-02 | Helper | 6 | 550
2026-10-02 | Carpenter | 2 | 950
2026-10-02 | Bar bender | 2 | 850
2026-10-03 | Mason | 2 | 900
2026-10-03 | Helper | 6 | 550
2026-10-03 | Carpenter | 2 | 950
2026-10-03 | Bar bender | 2 | 850
2026-10-05 | Mason | 2 | 900
2026-10-05 | Helper | 6 | 550
2026-10-05 | Carpenter | 2 | 950
2026-10-05 | Bar bender | 2 | 850
2026-10-06 | Mason | 2 | 900
2026-10-06 | Helper | 6 | 550
2026-10-06 | Carpenter | 2 | 950
2026-10-06 | Bar bender | 2 | 850
2026-10-07 | Mason | 2 | 900
2026-10-07 | Helper | 6 | 550
2026-10-07 | Carpenter | 2 | 950
2026-10-07 | Bar bender | 2 | 850
2026-10-08 | Mason | 4 | 900
2026-10-08 | Helper | 6 | 550
2026-10-08 | Carpenter | 2 | 950
2026-10-08 | Bar bender | 2 | 850
2026-10-09 | Mason | 4 | 900
2026-10-09 | Helper | 6 | 550
2026-10-09 | Carpenter | 2 | 950
2026-10-09 | Bar bender | 2 | 850
2026-10-10 | Mason | 4 | 900
2026-10-10 | Helper | 6 | 550
2026-10-10 | Carpenter | 2 | 950
2026-10-10 | Bar bender | 1 | 850
2026-10-12 | Mason | 4 | 900
2026-10-12 | Helper | 6 | 550
2026-10-12 | Bar bender | 1 | 850
2026-10-13 | Mason | 4 | 900
2026-10-13 | Helper | 6 | 550
2026-10-13 | Bar bender | 1 | 850
2026-10-14 | Mason | 4 | 900
2026-10-14 | Helper | 6 | 550
2026-10-14 | Bar bender | 1 | 850
2026-10-15 | Mason | 4 | 900
2026-10-15 | Helper | 6 | 550
2026-10-15 | Bar bender | 1 | 850
2026-10-16 | Mason | 4 | 900
2026-10-16 | Helper | 6 | 550
2026-10-16 | Bar bender | 1 | 850

## Cost report
Budget vs actual (October)
Actual comes from Materials and Labour. Variance = budget − actual.
Cost head | Budget (₹) | Actual (₹) | Variance (₹) | % used
420000
150000
45000
10000
Total
Trade | Man-days | Amount (₹)

## RA bill
Printable running account (RA) bill
Gross = this bill from BOQ. Retention and TDS are worked out on the gross before GST. Print A1:C18.
Bagale Constructions, Kolhapur
RA bill no
Client
Bill date
Work done to date (₹)
Less: billed earlier (₹)
Gross this bill (₹)
Less: retention (₹)
Add: GST (₹)
Less: TDS by client (₹)
Net payable (₹)
Measured and checked by site engineer: ____________ Client: ____________

## Dashboard
Site dashboard: as of 17 October 2026
Formulas over BOQ, Cost report and RA bill.
Contract value | Work done | RA bill net payable | October cost | Budget used | Heads over budget