## Read me
Event management system
Made-up data: every name, amount, shop and date in this file is made up for practice. Replace it with your own.
Yellow cells are inputs: type over them. Green cells hold formulas: do not type over them. Blue rows are headers and totals.
From ravindrabagale.com, Excel course, Excel Business Management Systems. By Ravindra Bagale.
Sheets: Setup, Expenses, Budget (estimate, client price, spent), Tasks, Quotation (printable), Client payments, Report (profit, cash), Dashboard.
GST rate in Setup B8 is an input; confirm the rate for your service with your accountant.
Log every vendor advance on the day you pay it.

## Setup
Event Management System: Setup (Zoya Events, Kolhapur)
Made-up event: a wedding reception for 400 guests on 20 November 2026. |  | Status | Owners
As-of date | 2026-10-17 | Not started | Zoya
Client | Ravina and Raja Patil | In progress | Salman
Event date | 2026-11-20 | Done | Rani
Guests | 400 |  | Raja
Margin on cost | 15%
GST on event service | 18%
Days to event

## Budget
Budget vs actual
Client price = estimate × (1 + margin). Spent comes from Expenses. Cost to plan with = the larger of estimate and spent.
Category | Estimate (₹) | Client price (₹) | Spent (₹) | Remaining (₹) | % used | Cost to plan (₹)
Venue | 150000
Catering | 340000
Decoration | 120000
Sound and lights | 60000
Photography | 75000
Invitations | 18000
Transport | 25000
Miscellaneous | 20000
Total

## Expenses
Expenses log
Every bill or advance paid to a vendor, one row each.
Date | Category | Detail | Amount (₹)
2026-10-02 | Venue | Hall advance | 75000
2026-10-05 | Catering | Caterer advance | 100000
2026-10-07 | Decoration | Flower order deposit | 40000
2026-10-08 | Invitations | Printing | 21500
2026-10-10 | Photography | Advance | 25000
2026-10-12 | Sound and lights | Advance | 20000
2026-10-14 | Miscellaneous | Trial tasting | 6000
2026-10-15 | Decoration | Stage frame | 38000
2026-10-16 | Venue | Second instalment | 50000

## Tasks
Task list
Overdue = due date before the as-of date and not Done.
Task | Owner | Due | Status | Days left | Flag
Book venue | Zoya | 2026-10-05 | Done
Final menu | Salman | 2026-10-15 | In progress
Print invitations | Rani | 2026-10-10 | Done
Send invitations | Rani | 2026-10-20 | Not started
Decor sketch approval | Zoya | 2026-10-12 | In progress
Sound check booking | Raja | 2026-10-14 | Not started
Guest transport plan | Raja | 2026-10-30 | Not started
Photographer brief | Zoya | 2026-11-10 | Not started
Seating chart | Salman | 2026-11-15 | Not started

## Quotation
Printable quotation
Client prices from Budget, GST from Setup. Print A1:D18.
Zoya Events, Kolhapur
Client |  | Event date
Item | Amount (₹)
Subtotal
GST
Total
Valid for 15 days. 40% advance to confirm.

## Client payments
Client payments
Money received from the client.
Date | Detail | Amount (₹) | Mode
2026-10-01 | Advance | 300000 | Bank transfer
2026-10-15 | Second instalment | 250000 | Bank transfer

## Report
Event profit and cash
Profit uses the cost to plan (estimate or spent, whichever is larger), so overruns reduce it.
Quoted, before GST
Cost to plan
Expected profit
Profit margin on quote
Received from client
Balance due from client (with GST)
Spent so far
Cash in hand for this event

## Dashboard
Event dashboard
Formulas over Budget, Tasks and Report.
Quotation total | Balance due from client | Budget used | Categories over budget | Overdue tasks | Days to event