## Read me
Engineers & PM
Made-up teaching data only. Names: Ravindra/Shraddha/Ruhi Bagale, Shahrukh, Amir, Salman, Zoya, Ravina, Raja, Rani. Cities: Pune, Solapur, Nashik, Sambhaji Nagar, Kolhapur, Nagpur.
EV/SPI are teaching proxies only.
Plant BOM/PM: Excel for Mechanical. OEE: Excel for Manufacturing.

## BOQ estimate
Item | Qty | Rate | Amount | Cont % | With cont
Civil package | 1 | 500000 |  | 5%
Electrical | 1 | 200000 |  | 8%
Instrumentation | 1 | 150000 |  | 10%
Total with contingency

## WBS tracker
Task | Owner | Start | Finish | % Complete | Status
Design freeze | Salman | 2026-09-01 | 2026-09-30 | 100%
Procurement | Raja | 2026-09-15 | 2026-10-20 | 70%
Site install | Amir | 2026-10-01 | 2026-10-25 | 40%
Formulas:
Status = IF(E2>=1,"Done",IF(TODAY()>[Finish],"Late","On track"))

## Plan vs actual
Task | Baseline finish | Actual finish | Delay days
Design freeze | 2026-09-30 | 2026-09-28
Procurement | 2026-10-10 | 2026-10-18

## Cost tracking
Package | Budget | Actual | Variance | % Complete | EV teaching
PKG1 | 500000 | 480000 |  | 90%
PKG2 | 200000 | 235000 |  | 50%

## CR log
CR | Description | Impact ₹ | Decision
CR01 | Extra cable tray | 35000 | Approved

## Formulas used
Cell | Formula | What it does
BOQ estimate!D2 | =B2*C2 | Qty*Rate
BOQ estimate!F2 | =D2*(1+E2) | Amount*(1+cont)
BOQ estimate!D3 | =B3*C3 | Qty*Rate
BOQ estimate!F3 | =D3*(1+E3) | Amount*(1+cont)
BOQ estimate!D4 | =B4*C4 | Qty*Rate
BOQ estimate!F4 | =D4*(1+E4) | Amount*(1+cont)
BOQ estimate!B6 | =SUM(F2:F4) | Sum with cont
WBS tracker!F2 | =IF(E2>=1,"Done",IF(TODAY()>D2,"Late","On track")) | Status
WBS tracker!F3 | =IF(E3>=1,"Done",IF(TODAY()>D3,"Late","On track")) | Status
WBS tracker!F4 | =IF(E4>=1,"Done",IF(TODAY()>D4,"Late","On track")) | Status
Plan vs actual!D2 | =C2-B2 | Delay days
Plan vs actual!D3 | =C3-B3 | Delay days
Cost tracking!D2 | =C2-B2 | Actual-Budget
Cost tracking!F2 | =B2*E2 | Budget*% complete
Cost tracking!D3 | =C3-B3 | Actual-Budget
Cost tracking!F3 | =B3*E3 | Budget*% complete