## Read me
IT & Consulting
Made-up teaching data only. Names: Ravindra/Shraddha/Ruhi Bagale, Shahrukh, Amir, Salman, Zoya, Ravina, Raja, Rani. Cities: Pune, Solapur, Nashik, Sambhaji Nagar, Kolhapur, Nagpur.
Util % = billed/available. RAID needs owners.

## Timesheet
Person | Project | Date | Hours | Billable
Ravindra Bagale | PRJ-01 | 2026-10-20 | 8 | Yes
Ravindra Bagale | Internal | 2026-10-21 | 4 | No
Salman | PRJ-01 | 2026-10-20 | 8 | Yes
Ruhi Bagale | PRJ-02 | 2026-10-20 | 6 | Yes
Billable hours

## Utilisation
Person | Available | Billed | Util %
Ravindra Bagale | 40 | 32
Salman | 40 | 40
Ruhi Bagale | 40 | 30

## Resource plan
Person | Project | Alloc % | Start | End
Salman | PRJ-01 | 60% | 2026-10-01 | 2026-12-31
Salman | PRJ-02 | 50% | 2026-10-01 | 2026-11-30
Ruhi Bagale | PRJ-02 | 80% | 2026-10-01 | 2026-12-31
Salman alloc sum
Flag

## RAID
ID | Type | Title | Owner | Raised | Due | Status | Days open
R1 | Risk | UAT delay | Salman | 2026-10-10 | 2026-10-30 | Open
I1 | Issue | VPN down | Raja | 2026-10-22 | 2026-10-23 | Open
D1 | Decision | Go-live date | Ravindra Bagale | 2026-10-15 | 2026-10-20 | Closed
Formulas:
Days open = TODAY()-[Raised]

## Status
Project | RAG | % Complete | Blocker
PRJ-01 | Amber | 65% | UAT env

## SOW
SOW | Value | Billed | Remaining
SOW-100 | 1000000 | 650000

## Formulas used
Cell | Formula | What it does
Timesheet!B8 | =SUMIF(E2:E5,"Yes",D2:D5) | Sum billable
Utilisation!D2 | =C2/B2 | Billed/Available
Utilisation!D3 | =C3/B3 | Billed/Available
Utilisation!D4 | =C4/B4 | Billed/Available
Resource plan!B7 | =SUMIF(A2:A4,"Salman",C2:C4) | Sum allocation
Resource plan!B8 | =IF(B7>1,"Over","OK") | Overallocate flag
RAID!H2 | =TODAY()-E2 | Days open
RAID!H3 | =TODAY()-E3 | Days open
RAID!H4 | =TODAY()-E4 | Days open
SOW!D2 | =B2-C2 | SOW-Billed