## Read me
Interior design costing system
Made-up data: every name, amount, shop and date in this file is made up for practice. Replace it with your own.
Yellow cells are inputs: type over them. Green cells hold formulas: do not type over them. Blue rows are headers and totals.
From ravindrabagale.com, Excel course, Excel Business Management Systems. By Ravindra Bagale.
Sheets: Setup (rate card, contingency, design fee, GST), Estimate, Site expenses, Summary, Payments, Quotation (printable), Dashboard.
Measure on site before you estimate; the quantities drive everything else.
Book every bill against a room on Site expenses so budget vs actual stays true.

## Setup
Interior Design Costing System: Setup (Ruhi Interiors, Nagpur)
Made-up rate card, estimate, site expenses and payments for one 2 BHK flat. GST rate is an input; confirm it with your accountant.
As-of date | 2026-10-17
Contingency | 5%
Design fee | 8%
GST | 18%
Project | Bagale flat, 2 BHK, Nagpur
Item | Unit | Material rate (₹) | Labour rate (₹) | Rate (₹) | Rooms
Modular kitchen | sq ft | 1300 | 500 |  | Kitchen
Wardrobe | sq ft | 1000 | 400 |  | Living room
TV unit | sq ft | 900 | 350 |  | Bedroom 1
False ceiling | sq ft | 75 | 35 |  | Bedroom 2
Painting | sq ft | 14 | 10
Wallpaper | roll | 2200 | 400
Light point | point | 650 | 150
Floor tiles | sq ft | 90 | 40

## Estimate
Estimate lines
One row per item per room. Rates come from the rate card.
Room | Item | Qty | Unit | Material (₹) | Labour (₹) | Amount (₹)
Kitchen | Modular kitchen | 85
Kitchen | Light point | 4
Kitchen | Painting | 220
Living room | TV unit | 40
Living room | False ceiling | 180
Living room | Painting | 650
Living room | Light point | 8
Living room | Wallpaper | 3
Bedroom 1 | Wardrobe | 56
Bedroom 1 | False ceiling | 140
Bedroom 1 | Painting | 480
Bedroom 1 | Light point | 5
Bedroom 2 | Wardrobe | 42
Bedroom 2 | Painting | 420
Bedroom 2 | Light point | 4
Bedroom 2 | Floor tiles | 120
Total

## Site expenses
Site expenses
Actual money spent per room: material and labour bills.
Date | Room | Description | Amount (₹)
2026-08-12 | Kitchen | Carcass and shutters, advance | 60000
2026-08-20 | Kitchen | Hardware and fittings | 22000
2026-08-28 | Living room | Ceiling material | 9800
2026-09-02 | Bedroom 1 | Wardrobe plywood | 38000
2026-09-08 | Living room | TV unit carpenter | 14000
2026-09-15 | Kitchen | Installation labour | 41000
2026-09-20 | Bedroom 2 | Wardrobe plywood | 30000
2026-09-28 | Living room | Paint and labour | 16500
2026-10-05 | Bedroom 1 | Ceiling and paint | 21000
2026-10-09 | Bedroom 2 | Tiles and labour | 16200
2026-10-14 | Bedroom 1 | Wardrobe laminate and labour | 23000
2026-10-16 | Living room | Wallpaper | 8100
2026-10-16 | Kitchen | Chimney and hob fitting | 25000

## Summary
Room summary, budget vs actual and quotation totals
Used % = actual ÷ estimate. Over budget when actual is above the estimate.
Room | Estimate (₹) | Actual so far (₹) | Variance (₹) | Used % | Flag
Total
Work estimate (₹)
Contingency (₹)
Design fee (₹)
Taxable (₹)
GST (₹)
Grand total (₹)

## Payments
Client payment schedule
Amount = grand total × milestone %. Status from due date and received date.
Milestone | Share | Amount (₹) | Due date | Received on | Status
Booking | 10% |  | 2026-08-10 | 2026-08-10
Material order | 40% |  | 2026-08-25 | 2026-08-27
Installation | 40% |  | 2026-10-10
Handover | 10% |  | 2026-10-30
Total

## Quotation
Printable quotation
Room totals and the final amount for the client. Print A1:C16.
Ruhi Interiors, Nagpur
Project
Room | Amount (₹)
Contingency (₹)
Design fee (₹)
GST (₹)
Grand total (₹)
Valid for 30 days. Payment as per the schedule on the Payments sheet.

## Dashboard
Interior project dashboard
Formulas over Summary and Payments.
Grand total | Work estimate | Spent so far | Budget used | Received from client | Rooms over budget