## Read me
Manufacturing production planning system
Made-up data: every name, amount, shop and date in this file is made up for practice. Replace it with your own.
Yellow cells are inputs: type over them. Green cells hold formulas: do not type over them. Blue rows are headers and totals.
From ravindrabagale.com, Excel course, Excel Business Management Systems. By Ravindra Bagale.
Sheets: Setup (machines, products, shift, efficiency), Orders (plan), Production log, Report, Job order (printable), Dashboard.
Type a planned start for every order; the sheet works out the finish date and warns when it is after the due date.
Sunday is the weekly off. Change the weekend code in Orders J5 if your factory works differently.

## Setup
Manufacturing Production Planning System: Setup (Salman Engineering Works, Sambhaji Nagar)
Made-up machines, products, orders and production for October 2026. Sunday is the weekly off.
As-of date | 2026-10-17
Shift hours per day | 8
Machine efficiency | 85%
Steel rate per kg (₹) | 85
Reject alert above | 3%
Machine | Number of machines | Hours per day
CNC lathe | 2
Power press | 1
Product | Machine | Cycle time (min) | Steel per unit (kg)
Flange F50 | CNC lathe | 6 | 1.2
Bush B20 | CNC lathe | 3 | 0.4
Shaft S30 | CNC lathe | 9 | 2.1
Bracket K10 | Power press | 1.5 | 0.8
Plate P15 | Power press | 1 | 0.6

## Orders
Orders and plan
Hours = qty × cycle time ÷ 60. Days = hours ÷ machine hours per day, rounded up. Finish skips Sundays (WORKDAY.INTL with weekend code 11).
Order no | Customer | Product | Qty | Due date | Planned start | Machine | Hours needed | Days needed | Planned finish | Plan check | Steel (kg) | Steel cost (₹) | Good made | Rejects | Balance qty | Progress | Status
| Raja Pumps | Flange F50 | 600 | 2026-10-08 | 2026-10-01
| Zoya Motors | Bush B20 | 1500 | 2026-10-12 | 2026-10-07
| Amir Agro | Bracket K10 | 3000 | 2026-10-10 | 2026-10-01
| Salman Fabricators | Shaft S30 | 400 | 2026-10-22 | 2026-10-14
| Ravina Engineering | Plate P15 | 2000 | 2026-10-24 | 2026-10-15
| Raja Pumps | Flange F50 | 800 | 2026-10-27 | 2026-10-20
| Rani Industries | Bush B20 | 2000 | 2026-10-30 | 2026-10-27
| Shahrukh Auto | Bracket K10 | 1500 | 2026-10-31 | 2026-10-21
Formulas:
Planned finish = WORKDAY.INTL([Planned start],[Days needed]-1,11)

## Production log
Production log
One row per order per day: good pieces and rejects.
Date | Order no | Good | Rejects | Product
2026-10-01 | SO-101 | 120 | 2
2026-10-01 | SO-103 | 245 | 10
2026-10-02 | SO-101 | 120 | 2
2026-10-02 | SO-103 | 245 | 10
2026-10-03 | SO-101 | 120 | 2
2026-10-03 | SO-103 | 245 | 10
2026-10-05 | SO-101 | 120 | 2
2026-10-05 | SO-103 | 245 | 10
2026-10-06 | SO-101 | 120 | 6
2026-10-06 | SO-103 | 245 | 10
2026-10-07 | SO-102 | 250 | 5
2026-10-07 | SO-103 | 245 | 10
2026-10-08 | SO-102 | 250 | 5
2026-10-08 | SO-103 | 245 | 10
2026-10-09 | SO-102 | 250 | 5
2026-10-09 | SO-103 | 245 | 10
2026-10-10 | SO-102 | 250 | 5
2026-10-10 | SO-103 | 245 | 10
2026-10-12 | SO-102 | 250 | 5
2026-10-12 | SO-103 | 245 | 10
2026-10-13 | SO-102 | 250 | 6
2026-10-13 | SO-103 | 245 | 10
2026-10-14 | SO-103 | 255 | 10
2026-10-14 | SO-104 | 73 | 1
2026-10-15 | SO-104 | 73 | 1
2026-10-15 | SO-105 | 300 | 4
2026-10-16 | SO-104 | 74 | 2
2026-10-16 | SO-105 | 300 | 5

## Report
Machine load and quality
Load = hours of orders not yet completed ÷ hours available in the next 20 working days.
Machine | Open hours | Hours in 20 days | Load %
Product | Good | Rejects | Reject % | Alert
Total

## Job order
Printable job order for the shop floor
Type an order number in B4. Print A1:B16.
Salman Engineering Works, Sambhaji Nagar
Order no | SO-106
Customer
Product
Qty
Machine
Hours needed
Planned start
Planned finish
Due date
Steel to issue (kg)
Record good pieces and rejects at the end of each shift.

## Dashboard
Production dashboard: October 2026
Formulas over Orders and Report.
Open orders | Late on plan | CNC lathe load | Power press load | Reject % | Steel for open orders (kg)