## Read me
Software project management system
Made-up data: every name, amount, shop and date in this file is made up for practice. Replace it with your own.
Yellow cells are inputs: type over them. Green cells hold formulas: do not type over them. Blue rows are headers and totals.
From ravindrabagale.com, Excel course, Excel Business Management Systems. By Ravindra Bagale.
Sheets: Setup (as-of date, team rates, statuses, priorities, sprints), Tasks, Burndown, Risks, Report, Dashboard.
Add tasks below the last row; formulas in columns L to P must be copied down. Type remaining hours in Burndown column C at the end of each day.

## Setup
Software Project Management: Setup (billing app for a Nashik distributor)
Made-up project, people and rates. Lists here feed the drop-downs on the Tasks sheet.
As-of date | 2026-10-17 | Type =TODAY() to make it live; the example is fixed at 17-10-2026.
Project | Billing app, Nashik distributor
Hours budget | 520
Team member | Role | Cost per hour (₹) | Status | Priority | Sprint | Starts | Ends
Ravindra Bagale | Project manager | 1200 | Not started | High | S1 | 2026-10-01 | 2026-10-14
Shraddha Bagale | Developer | 900 | In progress | Medium | S2 | 2026-10-15 | 2026-10-28
Shahrukh | Developer | 800 | Done | Low | S3 | 2026-10-29 | 2026-11-11
Zoya | Tester | 600 | Blocked
Amir | Designer | 700

## Tasks
Task log (one row per task)
Type the yellow columns. Remaining, variance, overdue flag, days left and cost are formulas.
ID | Task | Module | Owner | Priority | Sprint | Start | Due | Estimate (hrs) | Actual (hrs) | Status | Remaining (hrs) | Variance (hrs) | Overdue? | Days left | Cost to date (₹)
T01 | Login and roles | Users | Shraddha Bagale | High | S1 | 2026-10-01 | 2026-10-06 | 24 | 28 | Done
T02 | Screen designs | Design | Amir | High | S1 | 2026-10-01 | 2026-10-08 | 32 | 30 | Done
T03 | Customer master | Masters | Shahrukh | Medium | S1 | 2026-10-05 | 2026-10-12 | 30 | 34 | Done
T04 | Product master | Masters | Shahrukh | Medium | S1 | 2026-10-07 | 2026-10-14 | 28 | 26 | Done
T05 | Test plan | Testing | Zoya | Medium | S1 | 2026-10-08 | 2026-10-14 | 16 | 18 | Done
T06 | Invoice screen | Billing | Shraddha Bagale | High | S2 | 2026-10-15 | 2026-10-22 | 40 | 22 | In progress
T07 | GST calculation | Billing | Shraddha Bagale | High | S2 | 2026-10-15 | 2026-10-16 | 24 | 26 | Done
T08 | Payment entry | Billing | Shahrukh | High | S2 | 2026-10-15 | 2026-10-21 | 32 | 12 | In progress
T09 | Stock update on sale | Inventory | Shahrukh | Medium | S2 | 2026-10-16 | 2026-10-24 | 30 | 6 | In progress
T10 | Print layout for invoice | Design | Amir | Medium | S2 | 2026-10-15 | 2026-10-16 | 16 | 9 | Blocked
T11 | Test billing flows | Testing | Zoya | High | S2 | 2026-10-20 | 2026-10-28 | 24 | 0 | Not started
T12 | Sprint reviews | Management | Ravindra Bagale | Low | S2 | 2026-10-15 | 2026-10-28 | 12 | 4 | In progress
T13 | Reports: sales by day | Reports | Shraddha Bagale | Medium | S3 | 2026-10-29 | 2026-11-04 | 28 | 0 | Not started
T14 | Outstanding report | Reports | Shahrukh | Medium | S3 | 2026-10-29 | 2026-11-05 | 24 | 0 | Not started
T15 | User training notes | Management | Ravindra Bagale | Low | S3 | 2026-11-01 | 2026-11-09 | 12 | 0 | Not started
T16 | Go-live checklist | Management | Ravindra Bagale | High | S3 | 2026-11-05 | 2026-11-11 | 8 | 0 | Not started

## Burndown
Sprint S2 burndown (15 to 28 October)
Ideal line falls evenly to zero. Type the remaining hours each evening in column C.
Sprint | S2
Hours planned
Date | Ideal remaining | Actual remaining
178
148
126

## Risks
Risk register
Score = probability × impact (1 to 5 each). 15+ High, 8 to 14 Medium, below 8 Low.
Risk | Probability (1-5) | Impact (1-5) | Score | Rating | Owner | What we will do
Client changes the invoice format late | 4 | 4 |  |  | Ravindra Bagale | Freeze the print layout in the S2 review
Developer on leave in S3 | 2 | 4 |  |  | Ravindra Bagale | Pair Shahrukh with Shraddha on reports
GST rule change during build | 2 | 3 |  |  | Shraddha Bagale | Keep the tax rate in a settings table
Printer driver issue at site | 3 | 2 |  |  | Amir | Test print at the client office early
Data migration errors | 3 | 5 |  |  | Shahrukh | Dry-run import with last month's data

## Report
Team and status report
COUNTIFS and SUMIFS over the Tasks sheet.
Owner | Tasks | Done | Estimate (hrs) | Actual (hrs) | Overdue | Cost to date (₹)
Total
Status | Tasks | Estimate (hrs)

## Dashboard
Project dashboard
Formulas over Tasks, Risks and Setup.
Tasks | Work done (by estimate) | Overdue tasks | Hours used of budget | Cost to date | Open high-priority | High risks