## Instructions
Government and NGO Excel Template (Schemes, Beneficiaries and Fund Utilisation)
All numbers in this workbook are fictional teaching data, not real company figures.
What this template is for
Purpose | Track every project or scheme with sanctioned budget, funds released, amount spent and beneficiaries reached, see utilisation % and cost per beneficiary by district and scheme, and keep a fund position by funding source.
Made by | Ravindra Bagale, Excel & Data Analytics trainer. Free template from ravindrabagale.com.
Sheets in this workbook
Dashboard | Six KPI cards and four charts.
Projects | Input table Projects. Utilisation %, Unspent Balance, Reach %, Cost per Beneficiary and Flag are formulas.
Funds Received | Input table Funds: every grant instalment and donation.
Calculations | District, scheme, fund position by source, and status summaries.
Lists | Districts, schemes, funding sources and status.
How to fill it (step by step)
Step 1 | Open Funds Received and add each grant instalment or donation: Date, Funding Source, Details, Amount.
Step 2 | Open Projects. For each project type Project ID, Start Date, Sanctioned Budget and Target Beneficiaries.
Step 3 | Pick District, Scheme, Funding Source and Status from the drop-downs.
Step 4 | Every month update Funds Released, Amount Spent and Beneficiaries Reached.
Step 5 | Yellow rows flag slow spending.
Step 6 | Open Dashboard for your monthly report to donors or the district office.
Start fresh with your own data
Step 1 | Go to the first input sheet. Click the second sample row, then press Ctrl + Shift + Down Arrow to select down to the last sample row.
Step 2 | Right-click the selection and choose Delete > Table Rows. One sample row stays, so the table and its green formula columns stay alive.
Step 3 | Type your first real row over the one sample row that is left (yellow cells only).
Step 4 | Type your next rows directly under the table. The table grows by itself and the green formula columns fill down automatically.
Step 5 | Repeat for every input sheet, then change the lists on the Lists sheet (cities, products, names) to your own values. Drop-downs follow the Lists sheet.
Step 6 | Open Dashboard. Cards and charts read the tables, so they now show your data.
Colour key and protection
Yellow cells | Inputs. Type here or pick from the drop-down.
Green cells | Formulas. Do not type over them.
Protection | Calculations and Dashboard are protected without a password so formulas are not deleted by mistake. To change them: Review > Unprotect Sheet (no password needed). Input sheets are not protected, so the tables can grow.
Guide | Full guide with formulas: https://ravindrabagale.com/guides/excel-template-government-ngo.html

## Dashboard
Rani Seva Foundation: projects, beneficiaries and funds (FY 2026-27)
All numbers in this workbook are fictional teaching data, not real company figures. Cards and charts are formulas: change the input sheets and they update.
Projects | Sanctioned | Spent | Utilisation % | Beneficiaries reached | Cost per beneficiary

## Projects
Project and beneficiary register
Yellow columns: type or pick from the drop-down. Green columns: formulas, do not type over them. All numbers in this workbook are fictional teaching data, not real company figures.
Project ID | District | Scheme | Funding Source | Start Date | Status | Sanctioned Budget | Funds Released | Amount Spent | Target Beneficiaries | Beneficiaries Reached | Utilisation % | Unspent Balance | Reach % | Cost per Beneficiary | Flag
PR-101 | Nagpur | Skill Training | Government Grant | 2026-08-14 | Ongoing | 902000 | 541000 | 268100 | 150 | 97
PR-102 | Solapur | School Kits | CSR Grant | 2026-01-05 | Ongoing | 971000 | 728000 | 648500 | 1000 | 331
PR-103 | Sambhaji Nagar | Skill Training | Individual Donations | 2025-10-16 | Completed | 662000 | 662000 | 623100 | 80 | 74
PR-104 | Kolhapur | Water Projects | Individual Donations | 2026-02-28 | Ongoing | 700000 | 525000 | 327100 | 300 | 204
PR-105 | Sambhaji Nagar | Health Camps | CSR Grant | 2025-10-16 | Completed | 458000 | 458000 | 434000 | 800 | 800
PR-106 | Nagpur | Health Camps | CSR Grant | 2026-06-16 | Ongoing | 154000 | 92000 | 28300 | 300 | 152
PR-107 | Nashik | Skill Training | CSR Grant | 2026-03-04 | Completed | 1714000 | 1714000 | 1620500 | 200 | 205
PR-108 | Kolhapur | Water Projects | CSR Grant | 2025-11-07 | Completed | 200000 | 200000 | 190900 | 80 | 76
PR-109 | Nagpur | School Kits | Government Grant | 2026-06-08 | Ongoing | 650000 | 325000 | 283600 | 500 | 159
PR-110 | Kolhapur | Health Camps | Government Grant | 2026-03-27 | Completed | 276000 | 276000 | 271000 | 500 | 502
PR-111 | Pune | Health Camps | CSR Grant | 2026-01-18 | Planned | 164000 | 0 | 0 | 500 | 0
PR-112 | Nagpur | School Kits | Government Grant | 2026-01-14 | Completed | 897000 | 897000 | 876200 | 800 | 832
PR-113 | Sambhaji Nagar | School Kits | Government Grant | 2026-01-30 | Ongoing | 335000 | 251000 | 217400 | 300 | 213
PR-114 | Kolhapur | Health Camps | CSR Grant | 2026-06-18 | Planned | 211000 | 0 | 0 | 500 | 0
PR-115 | Nagpur | Water Projects | Individual Donations | 2026-03-09 | Completed | 183000 | 183000 | 180000 | 80 | 76
PR-116 | Nashik | Women SHG Support | Individual Donations | 2026-02-21 | Ongoing | 1826000 | 913000 | 582400 | 300 | 119
PR-117 | Sambhaji Nagar | Women SHG Support | CSR Grant | 2025-10-08 | Ongoing | 1341000 | 1005000 | 525500 | 200 | 76
PR-118 | Solapur | Health Camps | Individual Donations | 2025-11-12 | Completed | 112000 | 112000 | 111300 | 300 | 312
PR-119 | Pune | School Kits | Government Grant | 2026-01-24 | Completed | 1313000 | 1313000 | 1219200 | 1000 | 953
PR-120 | Kolhapur | Water Projects | CSR Grant | 2026-04-27 | Planned | 105000 | 0 | 0 | 50 | 0
PR-121 | Solapur | Skill Training | Individual Donations | 2025-11-25 | Completed | 566000 | 566000 | 546800 | 80 | 82
PR-122 | Nagpur | Health Camps | Government Grant | 2026-08-10 | Ongoing | 470000 | 352000 | 269600 | 800 | 582
PR-123 | Pune | Skill Training | CSR Grant | 2026-06-14 | Ongoing | 610000 | 305000 | 102500 | 80 | 37
PR-124 | Pune | Water Projects | Government Grant | 2026-07-26 | Ongoing | 90000 | 67000 | 44000 | 50 | 18
PR-125 | Pune | School Kits | CSR Grant | 2026-08-03 | Completed | 1004000 | 1004000 | 996200 | 1000 | 1063
PR-126 | Sambhaji Nagar | Health Camps | Government Grant | 2026-08-26 | Ongoing | 337000 | 202000 | 142600 | 800 | 379
PR-127 | Sambhaji Nagar | School Kits | CSR Grant | 2026-08-10 | Completed | 1044000 | 1044000 | 997500 | 1000 | 910
PR-128 | Sambhaji Nagar | Women SHG Support | Individual Donations | 2025-11-11 | Planned | 1380000 | 0 | 0 | 200 | 0
PR-129 | Nagpur | School Kits | CSR Grant | 2025-12-09 | Planned | 331000 | 0 | 0 | 300 | 0
PR-130 | Sambhaji Nagar | School Kits | CSR Grant | 2026-07-22 | Completed | 959000 | 959000 | 929400 | 800 | 803
PR-131 | Sambhaji Nagar | Water Projects | Individual Donations | 2025-12-16 | Ongoing | 540000 | 405000 | 160200 | 300 | 102
PR-132 | Solapur | Water Projects | Government Grant | 2025-10-25 | Completed | 343000 | 343000 | 338800 | 200 | 207
PR-133 | Kolhapur | Water Projects | Individual Donations | 2026-06-05 | Ongoing | 130000 | 78000 | 33700 | 80 | 61
PR-134 | Nagpur | Women SHG Support | CSR Grant | 2026-04-05 | Ongoing | 1045000 | 783000 | 434300 | 200 | 87
PR-135 | Pune | Women SHG Support | Government Grant | 2026-04-16 | Completed | 418000 | 418000 | 385600 | 100 | 92
PR-136 | Pune | Health Camps | CSR Grant | 2026-01-27 | Ongoing | 169000 | 126000 | 72500 | 300 | 104
PR-137 | Nashik | School Kits | Government Grant | 2026-03-01 | Completed | 280000 | 280000 | 267700 | 300 | 305
PR-138 | Solapur | Skill Training | CSR Grant | 2026-03-01 | Ongoing | 303000 | 227000 | 195100 | 50 | 34
PR-139 | Pune | Women SHG Support | Individual Donations | 2025-10-16 | Completed | 1828000 | 1828000 | 1785000 | 300 | 304
PR-140 | Nagpur | Health Camps | Government Grant | 2026-02-14 | Planned | 273000 | 0 | 0 | 800 | 0

## Funds Received
Funds received (grants and donations)
Yellow columns: type or pick from the drop-down. Green columns: formulas, do not type over them. All numbers in this workbook are fictional teaching data, not real company figures.
Date | Funding Source | Details | Amount
2026-04-10 | CSR Grant | Grant from a partner company (fictional) | 1500000
2026-05-02 | Government Grant | District scheme instalment 1 | 1200000
2026-05-20 | Individual Donations | Online donations May | 180000
2026-06-15 | CSR Grant | Grant instalment 2 | 900000
2026-07-05 | Individual Donations | Donation drive Pune | 240000
2026-07-28 | Government Grant | District scheme instalment 2 | 800000
2026-08-18 | Individual Donations | Online donations Aug | 150000
2026-09-09 | CSR Grant | Grant instalment 3 | 600000

## Calculations
Calculations
Every number on this sheet is a formula that reads the input tables. The sheet is protected without a password: Review > Unprotect Sheet if you want to edit. All numbers in this workbook are fictional teaching data, not real company figures.
District summary
District | Projects | Sanctioned | Released | Spent | Utilisation % | Beneficiaries
Total
Scheme summary
Scheme | Spent | Beneficiaries | Cost per Beneficiary
Total
Fund position by source
Funding Source | Received | Released to Projects | Balance in Hand
Total
Project status
Status | Projects
Total

## Lists
Lists and settings
Drop-down lists read these columns. Add a new value at the bottom of a list and it appears in the drop-downs. All numbers in this workbook are fictional teaching data, not real company figures.
City | Scheme | Funding Source | Status
Pune | Skill Training | CSR Grant | Planned
Solapur | Women SHG Support | Government Grant | Ongoing
Nashik | School Kits | Individual Donations | Completed
Sambhaji Nagar | Health Camps
Kolhapur | Water Projects
Nagpur